## Ark1
GANTT Chart
Project Month | Date | Year | Country | Event | Task
1 | Oct | 2009 | Finland | Kick Off Meeting | Presentation of the concept of Forum Theatre. Conceptdelvelopment for Cources for Guidance counsllors: Identifying the need, content, developing training modules for pilot testing, delveping training materials for pilot testing, translating, printing/publication of training materials. Website delveopment.
2 | Nov | 2009 |  |  | Finding target group for pilottesting
3 | Dec | 2009
4 | Jan | 2010 |  |  | Pilot testing of the course
5 | Feb | 2010 |  |  | revise/evaluate on pilot testing
6 | March | 2010
7 | April | 2010 | Denmark | 2nd Meeting, half way conference | day 1: Guest lecturer + guest (guidance counsellors from DK). Day 2: presentation of the final guidance counseller training course adjusted to de 3 countries and thier target groups).
8 | May | 2010
9 | June | 2010
10 | July | 2010
11 | Aug | 2010 | DK, UK and Fin | 1st training course | Holding training courses,
12 | Sep | 2010
13 | Oct | 2010
14 | Nov | 2010 | U.K | 3rd Meeting | Evaluate on the first training course + preparing the next training course. Publication, dissemination, website, facebook, blog
15 | Dec | 2010
16 | Jan | 2011
17 | Feb | 2011 |  | 2nd training course | Holding training courses
18 | March | 2011
19 | April | 2011 | DK, UK and Fin | Evaluation | evaluate on the training courses
20 | May | 2011
21 | June | 2011
22 | July | 2011
23 | Aug | 2011 | Denmark | Final Meeting, Final Conference | Final conference, Evaluation on the project, publication, dissemination, website
24 | Sep | 2011

## Ark2
LEONARDO TRANSFER OF INNOVATION
Propject title: |  | Wastage off Through the Stage: Forum Theatre in Carrier & Guidance Counselling for the Youth
Acronym: |  | ACTVICE
|  | Project Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
| Lead Responsible | Actual Month | 2010 Oct | 2010 Nov | 2010 Dec | 2011 Jan | 2011 Feb | 2011 Mar | 2011 Apr | 2011 May | 2011 June | 2011 July | 2011 Aug | 2011 Sep | 2011 Oct | 2011 Nov | 2011 Dec | 2012 Jan | 2012 Feb | 2012 Mar | 2012 Apr | 2012 May | 2012 June | 2012 July | 2012 Aug | 2012 Sep
Activity/Event
Kick Off Meeting | bar: 1
Minutes of Meetings | VIFIN | bar: 2
2nd Meeting, Seminar with FT Expert | bar: 8
Minutes of Meetings | VIFIN | bar: 9
3rd Meeting | bar: 16
Minutes of Meetings | VIFIN | bar: 17
4th and final Meeting + Final Conference | bar: 23
Minutes of Meetings | VIFIN | bar: 24
Needs analysis | UU, HUMAK, LBHF | bar: 2 to 3
Identifying target group for pilottesting | UU | bar: 2 to 3
Developing course materials and module | UU + All | bar: 3 to 4
Pilot test course | UU | bar: 4 to 5
Revise/evaluate pilot testing | UU | bar: 6 to 7
Translation of course material and module | HUMAK, UU | bar: 8 to 9
Presentation of the final guidance counseller training course | bar: 8
Holding training courses 1 (DK, FI, UK) | All | bar: 10 to 12
Holding training courses 2 | UU, VIFIN,FTR | bar: 16 to 18
Evaluation of the FT preformance + pre-test of the method | bar: 19 to 20
Evaluation of the participants (counsellors/teachers + students) | bar: 6; 10 to 12; 16 to 17; 19 to 20
Impact Evaluation of First group of student participants in FT | bar: 22 to 23
Mid-term Evaluation |  |  | 12: Submit Report
Final evaluation |  |  | 23: Submit Report
Writing/editing the materials for website | VIFIN | bar: 20 to 24
Production of brochures | VIFIN | bar: 16 to 23
Production of Final product: Handbook | All | bar: 14 to 24
Writing handbook | All | bar: 14 to 17
Editing handbook | LBHF | bar: 18
Graphic design & Layout of Handbook | VIFIN | bar: 15 to 16
Translation of handbook | VIFIN,HUMAK | bar: 19 to 20
Production and distribution | VIFIN, All | bar: 21 to 24
Website development + maintainance | VIFIN | bar: 5 to 24
Start a web-social network (Facebook) + maintainance | VIFIN
Writing content for website | VIFIN, All
Graphic design | VIFIN
Translation of website content | HUMAK; VIFIN
Blogging | All | bar: 5 to 24
Dissemination | All
Arrange for media exposure | FTR, LBHF, all
Dissemination at EU level | FTR, VIFIN | bar: 3; 13; 22 to 24
Newsletter | FTR, all | bar: 8; 13; 19; 23
Translation of newsletter | HUMAK; VIFIN | bar: 9; 14; 20; 24
Policy recommendations | ALL | bar: 23 to 24
Distribution of final products and results | All | bar: 22 to 24
Networking | All
Progress report | VIFIN | bar: 13
Financial report | VIFIN | bar: 13; 23 to 24
Final report | VIFIN | bar: 23 to 24