Minutes of meeting - Forum Theatre – Actvise

Kick Off Meeting Helsinki

2nd November 2010

Present:

VIFIN		Elizabeth Gregersen, Anette Grunnet

UU-Vejle		Anne Henriksen, Nadja Nielsen, Sine Bjerre Martinussen

HUMAK		Timo Sorvoja, Sanna Pekkinen, Katri Kaalikoski

LBHF		Diana Edgecombe

FTR		Mads Henning Pedersen

External evaluator	Nors Jackson

Welcome by Katri Kaalikoski (administrative director at HUMAK)

Presentation & introduction of HUMAK

- Small university but the largest in its field. Work nationwide and has 9 campuses with a total of 1500 students. Works in civic activities and youth work

- The Forum Theatre project will be a part of their cultural management degree.

Discussion of & rearrangement of agenda and schedule according to logistics and practical arrangements

Presentation of partners:

VIFIN by Elizabeth Gregersen

- Resource Centre for Integration. Works with implementing programs on national, regional and local level. Work and projects focused around integration.

- Explaining VIFINs organisation within the municipality and the board of VIFIN.

London Borough of Hammersmith and Fulham by Diana Edgecombe

- Further Education (FE) colleges in the borough have about 20000 pupils. Also there are a lot of larger companies in the area, BBC, Walt Disney Company, L’oreal, Leo Burnett.

- Working with preparing pupils for work and education. Age group 0-19, focus is on 14- 19 year olds. Work with mentoring programmes. Key priority is giving effective information, advice and guidance.

UU-Vejle by Anne Henriksen

- 15 counsellors at UU in Vejle. A youth guidance centre. Works with youth in the transition from compulsory education to youth education. From 7th grade.

- Aims: Targeting pupils with special needs/guidance, with drop outs. Ensure readiness for education. Age group 13- 25 (if they haven’t finished a youth education).

- Network is public services and departments, counsellors, social workers, local businesses and institutions.

FTR by Mads Henning Pedersen

- Founded in 2005. Working in both firms and public sector.

- Introduction to some of the pedagogy FTR works with. Forum Theatre taking the starting point in dilemmas. About reflection – meaning and interpretation – what makes you think what you think and do.

COMMON DINNER

Wednesday 3rd November

Present:

VIFIN		Elizabeth Gregersen, Anette Grunnet

UU-Vejle		Anne Henriksen, Nadja Nielsen, Sine Bjerre Martinussen

HUMAK		Timo Sorvoja, Sanna Pekkinen, Risto Ruottunen

LBHF		Diana Edgecombe

FTR		Mads Henning Pedersen

External evaluator	Nors Jackson

Presentation of the Minerva Project An Educational Dimension of Conflict Resolution Through Cultural Production by Humak, Timo and Risto Ruottunen (Theatre Director and drama coach, M.A.)

- Had worked with Forum Theatre method with migrants. The Minerva project was developed. Developed as distance learning. Using videos, videoconferences, video lectures, and new technology in general.

- Humak was the project coordinator. Target groups were cultural minorities

Explaining Forum Theatre:

- Democratic Theatre. Gives spectators a chance to find their own style and stories to work with.

- Watching a demonstration video of a FT performance made in relation to the project (Lectures and demonstrations can be found on the website of actandchange.eu under the submenu of Norway and Finland).

Sanna Pekkinen from HUMAK told about her experiences with using the materials from the Minerva project as a non-expert on FT.

- Used the method of the project working with cultural studies.

Discussion about the term The Joker

- Many in the group feels that the term ‘Joker’ has a negative connotation and that it could hinder the process of FT when working with young people. Should consider another name for the joker for this project.

Recommended Books:

- Augusto Boal: Games for Actors and Non-actors

- Augusto Boal: Legislative Theatre

- Augusto Boal: The Rainbow of Desire

- Playing Boal: Theatre, Therapy, Activism

Mads Henning Pedersen gave an introduction to Augusto Boal, the man.

- The background and motivation for developing the Forum Theatre method

LUNCH

Elizabeth going through key elements from the application

- Deliverables

- How we are going to do it

- Content

Presentation of the starting point for the project:

- Inspired by the Act & Change Minerva project

- Target groups in each country – are we still addressing the same target groups as put in the application? All partners DK, UK, FI agree that target groups are the same. Maybe including social educators.

- In UK the counsellors/teachers might be the learning mentors the borough is working with. Also includes business people – just a broader definition of people who do counselling.

Discussion of the M-counselling/ mobile perspective of the project:

- UK: Can not use FB in an interactive way because of legislation. Not legal to put images/videos of under 16 on a public site. Facebook can only be used as an informative site – as a root for information. Possible to link to another site if necessary.

- Need clarification still on how we will use the IT/web perspective and where in the course, etc. Mads Bo Kristensen at VIFIN will be the pedagogical supervisor for this.

Work Package I – Coordination & Management

Leader is VIFIN

Internal communication platform

- Will use HUMAK-pro, which is the intranet system of HUMAK. Can create a closed platform for the project there. 
HUMAK will create the forum, when getting emails of all from VIFIN

- Will add the participants at the meeting to this platform, plus a few others (1 more from UU, 1 from VIFIN, 1 from FTR.)

To have a continuous communication throughout the project, it is decided to make a quarterly report on the projects activities - will be set up against the milestones.

- Will include what we have done, etc.

- 1st report will be the end of January 2011

  - In addition to this, VIFIN will update the Gantt Chart and put the due dates into it.

Work Package II – Curriculum & Training Course

Leader UU- Vejle

Discussing the pilot test:

- The test is for counsellors, not teachers. The purpose of the pilot is to test if the training course module is good enough to use in real training courses.

UK: a 2-day course would not be possible with the target group they are working with. UK will find a way of breaking down the course, so that it can be run in a different way. Still at least 2 people from UK will be trained as trainers that will be able to teach the FT method to counsellors/teachers/mentors.

Thursday 4th November

Present:

VIFIN		Elizabeth Gregersen, Anette Grunnet

UU-Vejle		Anne Henriksen, Nadja Nielsen, Sine Bjerre Martinussen

HUMAK		Timo Sorvoja, Sanna Pekkinen

LBHF		Diana Edgecombe

FTR		Mads Henning Pedersen

External evaluator	Nors Jackson

Logistics of the day

Bringing back focus to the Minerva project

- The Act & Change project should be the starting point for this project

Going through the activities in WPII in detail from the start.

VIFIN will provide the framework for needs analysis to each partner (some questions to be answered)

The evaluation of the Minerva project would be useful

- Timo will send round the evaluation from Brussels

Internal evaluation material

- LBHF can provide some framework

- Timo will look into how Minerva was evaluated.

Discussing a steering group:

- project steering group is one representative from each partner + evaluator

- Will be bringing in key partners throughout the life of the project. Also involve them in meetings to create attention to the project.

- Discussion of a larger/broader steering group. Can be addressed again further on.

Pilot test:

- VIFIN takes the responsibility to be leader for the pilot test.

New plan for WPII

- Study the Act & Change material – focus on: Did I learn something? What? What else do I need to know?

  - Video, website, etc.

    - UU-Vejle, LBHF, Mads Bo (VIFIN).

- Develop Course

    - Sanna, Mads Bo, FTR- to be collected by Elizabeth

- Pilot test Jan/Feb.

  - Participants will be LBHF, UU-staff

    - Will be conducted by FTR, Sanna, Mads Bo (Nors observator?)

      - Will be followed by a UK-pilot, where LBHF tries out their method of constructing the course.

- All Evaluate the pilot

- Revising the course module & materials

    - Sanna, FTR, Mads Bo

- Run Courses

Date set for pilot test is February 22nd and 23rd in Denmark.

Work Package III – Mobile & IT-platform

- Website

  - A resource for information and materials

  - Will be a passive website without any interactive guidance features

- Facebook used as an information tool

VIFIN will present a proposal for graphic line by end of December.

Website should be running by February.

Domaine name: ACTVICE

Getting people to join the social network is a mutual responsibility of partners.

Blogging/ keeping FB current is also mutual responsibility.

Discussing the relevance of a blog:

- Conclusion: wont create a blog, since most of the partners are already able to say, that they wont update it to the extend it is needed to make a good blog.

Mads Henning will send around links to FT materials in Danish.

Work Package IV – Dissemination & Valorisation

Leader FTR

Mads presented his proposal for a dissemination plan

- Press releases

  - Story development

  - Content – the different milestones of the project

- Target groups

  - Unions, ministry of integration, ministry of education, educational institutions, counsellors, teachers associations, EU Leonardo, TV-stations, government departments.

Mads has contacts in TV and educators association

VIFIN will send out the first local press release through the municipality’s communication department

To All:

Keep copies of any news coverage, press releases, and mailing lists/mails.

Diana from LBHF presents how they will work with the project

This project relates to an Employee Volunteering project

Paul Hamlyn Foundation, Take Two Programme (working with the BBC)

- Works on the speaking and listening skills of youth

- Will offer training to all coordinators in FT-method.

- 2 Schools that are interested in the project, potential participants – have very dedicated progress tutors.

  - Girl school, large portion of Muslim girls, that are bullies cause they have been bullied. Boys school, 70% black minority ethnic.

LBHF has developed evaluation materials to all their activities that could be shared with the group for inspiration.

Diana will send a brief document about the Paul Hamly project – upload it on the communication platform.

Diana will most likely bring a colleague to the pilot test meeting in Denmark.

Evaluation by Nors Jackson

Gives an insight to her work experience – an evaluator with an informed perspective of the subject.

Evaluation of :

- the quality of the partnership

- results and products

- impact

- added value

Accountability

Processes

Formative evaluation

- Phone calls

- Surveys

- Paper based

Solution based perspective

Will make a detailed action plan with time frame

Will look at monitoring/paperwork

To all: Make notes of all meetings!

Record everything – related/secondary activity

Will look at value for money

To all:

Write down your own activity per work package

Diana can send a form for monitoring activities

Good idea to make notes and records of meetings and activities

Nors can function as facilitator of conflicts if necessary – will take it incident by incident

All: keep Nors aware of how things progress, to make the evaluation smoother

Break down their responsibilities, tasks and activities. ALL partners!

End of November from each – all agree!

Elizabeth presents the slides from IU (Danish national agency)

- ToI

  - Updating project

  - Transferring

  - Adapt

Return of contracts

- Received from Finland

- UK has sent mail with scanned copy of contract – Not received. (Received upon arrival back in DK).

Time Sheet

Consolidated time sheets sent by august 2011 to Elizabeth for the financial report

From All!

Keep them updated as we go along.

Time sheet accompanied by personal cost sheet

Finance and admin handbook  + Financial and administrative rules – all should read.

Going through the rules

NB. Please book in advance for travels

VIFIN distributed practical and informational materials on CD rom.

Logos –

- Leonardo logo (LLP) should be on all material!

- Send each partner logo to VIFIN in good quality

- VIFIN will send out a disclaimer text that should also be put on all published materials

VIFIN will send 1st payment when contract is signed and returned.