DISSEMINATION, EXPLOITATION & SUSTAINABILITY PLAN

- Definition of Terms /Objectives

The following definition will be applied to the project’s dissemination plan. The definition is culled from Survival Kit: Managing Multilateral Projects in Lifelong Learning Program:

Dissemination – a planned process of providing information on the quality, relevance and effectiveness of the results of programmes and initiatives to key actors. It occurs as and when the results of programmes and initiatives become available. This activity happens at both project and programme level, and involves the active participation of intermediary relay bodies.

This also implies that the project needs to conduct publicity from Month1 to Month 24, targeting the project’s stakeholders and target groups, in particular, and the public in general.

Exploitation consists of mainstreaming and multiplication. Mainstreaming is the planned process of transferring the successful results of programmes and initiatives to appropriate decision-makers in regulated local, regional, national or European systems. Multiplication is the planned process of convincing individual end users to adopt and/or apply the results of programmes and initiatives.

Sustainability is the capacity of the project to continue its existence and functioning beyond the end of the funded period. The project results are used and exploited continuously. Sustainability of results implies use and exploitation of results in the longer term.

To put the expectations of the Lifelong Learning Programme more concisely: A Multilateral Project should seek to promote the project, its processes and (interim and final) results from the beginning, make sure that the results reflect the needs of their envisaged users and are actually used by these groups, and make provisions for these results to have a lasting impact on the educational field concerned.

- Target Groups (primary & secondary)

Primary

Teachers, guidance counsellors & mentors

Decision makers in teachers’ colleges and primary/secondary schools

Political decision makers at national and local levels

Secondary

Young people

General public

- Key message (s)

Forum theatre offers an alternative method for a more effective guidance and motivation of young people to complete an education.

The project, Forum Theatre, offers teachers, mentors and guidance counsellors a chance to learn the forum theatre technique in motivating and providing career guidance to pupils and young people.

- Tools and milestones

- Website/blogs

www.actvice.eu

Regular news updates (at least every two months), from all partner organisations

Link to FB group

Denmark

www.vifin.dk (Quarterly)

www.vejle.dk (Quarterly)

http://www.vkintra.vejle.dk/page.aspx? (Webkatten) (Quarterly)

http://www.uuv.vejle.dk (Quarterly)

http://www.vejledigitaleskoler.net/ (blog of Mads Bo-Kristensen for Skoler I bevægelsen) (quarterly)

http://www.skolenibevaegelse.nu/ (Skoler i bevægelser, Vejle kommune) (Quarterly)

Finland

UK

- Facebook – at least monthly updates per partner

- Press releases – at least quarterly per partner

Denmark

Vejle Amts folkeblad

Uge avisen

Søndags avisen

Urban

Metro Express

Finland

UK

- Newsletter

Project newsletter – quarterly electronic; all articles link to the project website be posted on the project’s website

Vifin

- Articles special magazines and publication

Denmark

“Vejlederen”

Sprogforum

- Participation in events: fairs/conferences, seminars, festivals

- Presentation meeting to relevant stakeholders

- FT Seminar in Vejle

- Ggghghgt

- Ggghg

- bnhhnjhjh

Publicity Collaterals

Brochures

Posters

- Detailed plan per tool

- Developing a valorisation plan