Forum Theatre 2nd Management Meeting

Vejle

May 16th -18th 2011

Minutes of meeting

Attendees:

VIFIN	Elizabeth Gregersen, Anette Grunnet, Ib Jespersgaard (Day 1), Niels Ole Ankerstjerne (Morning session Day 1)

UU Vejle	Nadja Nielsen, Sine Bjerre Martinussen, Anne Henriksen (Morning sessions Day 1 and 3)

HUMAK		Timo Sorvoja

LBHF		Diana Edgecombe, Jon Chappell, John Horton

External evaluator	Nors Jackson

Day 1 – Monday May 16th

9:00 - 9.30	Final agreements on the agenda

Everyone agreed to try to work through on day 1 so the morning of day 2 could be used to reflexion and preparations for the seminar, and a meeting between HUMAK and VIFIN.

Levelling of expectations to the meeting:

The participants made comments that they expected the meeting to give them clarification of dates for the training courses and an overview of the targets and achievements needed done till January 2012 and the next meeting.

9:30 – 12.30	Overview – Coordinator + local partners

Update on partner activities:

VIFIN: Been disseminating the seminar and making preparations for it. Website is up and running in Danish and English, still need the Finnish translation. Alongside with the website, the first edition of the newsletter is out.

UU Vejle: Been doing a lot of networking, always get positive feedback. Had a group of counsellors from the UU Copenhagen, who were introduced to the project, the method of FT and some warm-up exercises. Sine also did a test run of the method with a class of 8th graders. Had very good results – the young people were very involved and into it. Also took some video footage of it.

UU have been discussing the possibility of using 2, maybe 3 schools in Vejle as ‘test schools’ or exemplary schools, where the method is introduced more intensely. Have also been working on producing materials for the course.

LBHF: Have adopted and adapted some scenarios from Boal. Found it difficult to apply Boals ideas directly to this project and target group, since Boal is very political, and focused on oppression. Partnership agreed that it would be a good idea to move away from/’soften’ the ‘oppressor/oppressed’ definition. This should be explained and elaborated on in our material and perhaps on the website as well; that we use an adapted version of Boals ideas.

The Take Two project has a working group meeting in the weeks following the management meeting, where LBHF have plans of introducing the FT method to school coordinators. LBHF suggested that it would be useful for them to informally call the project for example the Leonardo Theatre project, since Forum Theatre has a political connotation that might put some people off.

Have been researching on the possibility of attending a FT training course locally (perhaps Cardboard Citizens), so the LBHF representatives will be more knowledgeable of using FT. VIFIN agreed to have a look at the budget to see if such activities can be incorporated.

LBHF informed that the guidance services in UK are getting minimized and undergoing budget cuts. Their target group is instead volunteer networks (main priority), drama teachers, etc.

HUMAK: Not much activity happening at the moment. Sanna have been writing article for the internal newspaper of HUMAK. Also they are developing the new curricula for the university, and they are interested in new and varied methods, so FT could be an inspiration.

The participants of the HUMAK training course will be HUMAK students, and local school students.

Newsletter development and deadlines:

Newsletter format is agreed to work for all partners. The articles are posted straight on the website, and the newsletter template links to those. Articles are needed about 2-3 weeks in advance so they can be translated, then uploaded. First edition is out a bit delayed. According to the original plan, edition 2 should be sent out in June. Contributions from partners should be handed into VIFIN by the end of May. VIFIN will send out a reminder and ideas for articles.

Website:

The plan is to have all partners have access to the website. They will be given a log in and password, so they can make local updates to the website. All partners agree that some content should still be the same across countries, but that local information can differ.

VIFIN will make a short ‘how to’ manual to the CMS system.

Social networking sites and issues:

Use of Facebook in project: There will be made a project page for dissemination use, and aimed at practitioners. Partners discussed the different settings and privacy options that Facebook offer. It is agreed that there should be no ethical problems in having a Facebook page for professionals, as long as it is not a place to upload videos or personal information, or for mentors/counsellors to interact with young people.

Linked In is raised as an alternative that might have a more professional profile and could attract more professionals especially in the UK. Partnership will test both social platforms to see which one works best.

Updating the pages to make it active and relevant will be done at least monthly. All partners will be responsible for coming up with content, links, news, etc. for the pages, Anette/ VIFIN is responsible for reminding partners, and collect/post when needed.

Use of social networks/media in project:

Privacy issues regarding posting video material online. We can never fully control the distribution, but we can do the best to minimize it. Discussing Youtube with the potential of having private channels that can only be viewed when invited and logged in. Can be used as closed forums, managed by the teacher/counsellor/mentor, who can decide which comments are posted or not. All the options, settings, issues, ethics etc. will be outlined in the handbook and training course, so that the responsibility and level of privacy is left up to the user.

The IT-part of the training course will be facilitated by Niels Ole Ankerstjerne (NOA), who will be travelling to UK and FI for their courses. The content of the IT training will be developed by NOA and Mads Bo-Kristensen.

13.15 –16.00 Valorisation, dissemination and sustainability

Definition of valorisation: Dissemination + Exploitation = Valorisation

Valorisation throughout the project ensures Sustainability post project.

Dissemination (of products) = Aimed at target groups, publicity activities (media, articles, website, fairs, one-on-one meetings, etc.)

Exploitation= Training

At local, national and EU-level

Dissemination:

Valorisation form needed back completed from each partner for the interim report – Deadline mid September

Sustainability plan: Collate the local plans of each partner to create one common sustainability plan. Deadline End of June.

Elizabeth will upload an example of an Exit Plan.

Final inputs for the Dissemination plan still needed from HUMAK and UU Vejle, partners are also advised to provide a Gantt Chart of their local activities – End of June

Reporting

The interim report is due on 30th of September. For the report the project will need inputs from each partner on local activities done and planned, dissemination and target groups (description and numbers). Deadline 1st of September – deliver information to VIFIN who will put the report together. Accompanied by scanned/electronic copies of documentation.

Timesheets for the period from October 1st 2010 to September 30th 2011 have to be delivered by September 1st signed and stamped.

Personnel cost – The sheet should be filled by the financial department or the equivalent.

VAT-statement needed as well as bank transfer document (with the attached bank transfer receipt). Deadline September 1st.

Tuesday May 17th

12.30 –17.00	Forum Theatre theme event with Katrin Byréus

Evaluation forms will be summarized and shared by Anette.

Wednesday May 18th

9.00 – 12.30 	Discussion of final course/content

Short review of Tuesday’s event. Was generally good, but it was suggested that it would be an idea to give out materials for participants, so they have something to go back to their workplace with. Was agreed that we will do a follow up with the participants, giving them some more info and material – VIFIN will be responsible.

The need for a detailed lesson plan/teaching module was mentioned. One that describes the objective of and the methodology used in each session of the training course, and what the session aims at achieving.  UU and Risto (/Sanna) will be in charge of this – deadline is June 15th.

Course Materials: Review of materials we have and what we need to still develop.

Already produced:	A short history (from Sanna)

The structure of FT/ An Actvise Event/ Activities /The stage (UU)

Role of the Joker (UU)

Suggested Scenarios (LBHF)

Pedagogy of IT (VIFIN)

Everyone will read the materials and give comments by the end of May. Changes made and final versions to be ready by June 30th

Additional materials needed:	Warm up exercises (UU)	May 30th

Value exercises (UU)	May 30th

List of litteratur/materials  Sanna May 30th ?

IT manual 	VIFIN 	June 15th

Ethics 	VIFIN	June 15th

Comments to be made by June 15th (June 20th for the last two from VIFIN) and rewrites to be done by June 30th.

July is the summer holiday – VIFIN, UU, and HUMAK will be closed/unavailable for most of that month.

Translation of materials from July 1st – August 10th Deadline!

Course dates in the fall:				Follow-up day

Danish course 1: 	September 15th -16th 		October 26th

UK course:		September 22nd-23rd		Oct./Nov.?

Finnish course:	October 13th -14th ??		??

Danish course 2:	November 1st – 2nd 		December 6th

Partners are asked to confirm their local dates by end of May.

The partnership discussed the target group of participants in each country. LBHF is asked to provide a short statement on their target group, since it is slightly different from the proposal.

Invitation for the training course: VIFIN will provide the design, partners (LBHF and HUMAK) are asked to send VIFIN the text of an initial invitation/flyer (to make people save the date) at the end of May.

13.30 – 14.30 Effect and impact evaluation of project products

By LBHF & Nors Jackson

The evaluation of the projects products were discussed. How should we evaluate the training course and the materials/guidebook produced. The evaluation should be a continuous process through the project, and it is suggested to start by evaluating the website and newsletter already. A comment box can be made part of the website where viewers are able to make comments – VIFIN will look into the possibility.

Recording interest/inquiries, noting number of outside partnership countries involved. Record number of newsletters send. Analyse website statistics with Google analytics.

The evaluation methods discussed were evaluation of the training courses, follow up evaluation of the course participants after some time, impact evaluation in the form of samples of young people (mainly qualitative methods suggested as relevant).

LBHF will look at existing evaluation forms, adapt and update so they can be used for Forum Theatre. Will make a draft evaluation plan on which activities, when and how they should be evaluated – can be done by end of May.

Will make a draft training course evaluation – deadline August 15th, which gives time for comments and translation before the training course.

HUMAK will get hold of the evaluation report of the Act & Change project for inspiration on how to evaluate FT.

UU (Sine) will send an example/summary of the evaluation they use.

Interim evaluation report – presented by Nors. Agreement that the draft will be shared with VIFIN first, then the rest of the partnership.

Dates for management meeting 3 in January 2012 in London.

Preliminary agreement on the dates Wednesday 18th -21st of January (Wednesday and Saturday travel days, Thursday and Friday meeting days)

Products are: FT method; Training course and Handbook